## # Scan 1
Press Ctrl+Alt+Shift+F9 to recalculate all formulas!
Copy values from "New values" to "Old values" with date to see changes next time.
Task | IssueSummary | IssueKey | New values |  |  |  | Old values |  |  |  | Difference
|  |  | 02 Oct 2014 11:31 +04:00 |  |  |  | 02 Oct 2014 11:15 +04:00
|  |  | Estimation | Spent | Remaining | Status | Estimation | Spent | Remaining | Status | Estimation | Spent | Remaining | Status
Task pile #1 | Task #1 | PRJ-1 | 8 | 8 | 0 | Closed | 8 | 8 | 0 | Closed | 0 | 0 | 0 | 0
| Task #2 | PRJ-2 | 7 | 6 | 2 | In progress | 7 | 6 | 2 | Open | 0 | 0 | 0 | 1
| Task #3 | PRJ-3 | 8 | 5 | 3 | In progress | 6 | 3 | 3 | In progress | -2 | -2 | 0 | 0
| Task #4 | PRJ-4 | 9 | 4 | 4 | In progress | 5 | 2 | 3 | In progress | -4 | -2 | -1 | 0
| Task #5 | PRJ-5 | 7 | 3 | 5 | In progress | 7 | 1 | 6 | In progress | 0 | -2 | 1 | 0
| Task #6 | PRJ-6 | 8 | 17 | 0 | Closed | 8 | 17 | 0 | Closed | 0 | 0 | 0 | 0
| Total | skip | 47 | 43 | 14 | 75.44% | 41 | 37 | 14 | 72.55% | -6 | -6 | 0 | -2.89%
Task pile #2 | Task #7 | PRJ-7 | 16 | 11 | 0 | Closed | 16 | 11 | 0 | Closed | 0 | 0 | 0 | 0
| Task #8 | PRJ-8 | 15 | 10 | 1 | In progress | 14 | 9 | 3 | Open | -1 | -1 | 2 | 1
| Task #9 | PRJ-9 | 14 | 9 | 2 | In progress | 13 | 9 | 2 | In progress | -1 | 0 | 0 | 0
| Task #10 | PRJ-10 | 13 | 8 | 3 | In progress | 13 | 9 | 4 | In progress | 0 | 1 | 1 | 0
| Task #11 | PRJ-11 | 12 | 7 | 4 | Closed | 0 | 1.25 | 0 | Closed | -12 | -5.75 | -4 | 0
| Total | skip | 70 | 45 | 10 | 81.82% | 56 | 39.25 | 9 | 81.35% | -14 | -5.75 | -1 | -0.471%

## # Scan 2
Press Ctrl+Alt+Shift+F9 to recalculate all formulas!
Copy values from "New values" to "Old values" with date to see changes next time.
Task | IssueSummary | IssueKey | New values |  |  |  | Old values |  |  |  | Difference
|  |  | 02 Oct 2014 11:31 +04:00 |  |  |  | 02 Oct 2014 11:15 +04:00
|  |  | Estimation | Spent | Remaining | Status | Estimation | Spent | Remaining | Status | Estimation | Spent | Remaining | Status
Task pile #1 | Task #12 | PRJ-12 | 9 | 8 | 0 | Closed | 8 | 8 | 0 | Closed | -1 | 0 | 0 | 0
| Task #13 | PRJ-13 | 8 | 6 | 2 | In progress | 7 | 6 | 2 | Open | -1 | 0 | 0 | 1
| Task #14 | PRJ-14 | 9 | 5 | 3 | In progress | 6 | 3 | 3 | In progress | -3 | -2 | 0 | 0
| Task #15 | PRJ-15 | 10 | 4 | 4 | In progress | 5 | 2 | 3 | In progress | -5 | -2 | -1 | 0
| Task #16 | PRJ-16 | 8 | 3 | 5 | In progress | 7 | 1 | 6 | In progress | -1 | -2 | 1 | 0
| Task #17 | PRJ-17 | 9 | 17 | 0 | Closed | 8 | 17 | 0 | Closed | -1 | 0 | 0 | 0
| Total | skip | 53 | 43 | 14 | 75.44% | 41 | 37 | 14 | 72.55% | -12 | -6 | 0 | -2.89%
Task pile #2 | Task #18 | PRJ-18 | 17 | 11 | 0 | Closed | 16 | 11 | 0 | Closed | -1 | 0 | 0 | 0
| Task #19 | PRJ-19 | 16 | 10 | 1 | In progress | 14 | 9 | 3 | Open | -2 | -1 | 2 | 1
| Task #20 | PRJ-20 | 15 | 9 | 2 | In progress | 13 | 9 | 2 | In progress | -2 | 0 | 0 | 0
| Task #21 | PRJ-21 | 14 | 8 | 3 | In progress | 13 | 9 | 4 | In progress | -1 | 1 | 1 | 0
| Task #22 | PRJ-22 | 13 | 7 | 4 | Closed | 0 | 1.25 | 0 | Closed | -13 | -5.75 | -4 | 0
| Total | skip | 75 | 45 | 10 | 81.82% | 56 | 39.25 | 9 | 81.35% | -19 | -5.75 | -1 | -0.471%